## CryoEM
Paper | Task Name | Type | Due Date | Done | Status | Comments | Assigned To
- | Pthreaded code | D | 2016-12-20 | TRUE | Complete | Verify it's working and improving
weighting | Rewrite results section | W | 2016-12-24 | TRUE | Waiting to results | No simulations, just short comparison, then demonstration of nn02 wrt each other and reference.
weighting | Get more experiments | E | 2016-12-26 |  | Complete
- | Understand remote lags and fix it! | I | 2016-12-29 |  | Complete | gave up - using cellular remote and local static development instead
? | merge code into ASPIRE | D | 2016-12-29 |  | waiting to yoel | just needs to be finished together
weighting + ? | Best blocks analysis | R | 2016-12-31 |  | Not Started | we may be able to avoid it
cls detection | Cls convolution optimization | R | 2017-01-14 |  | Not Started | How to set weighted average?
cls detection | Recreate raw reconstruction | E | 2017-01-14 |  |  | N=10k, 89, masked, shuffled data, optimized cls convolution
cls detection | Efficient cls convolutional code | D | 2017-01-21 |  | Not Started
refinement + cls detection | Classic refinement | E | 2017-01-21
cls detection? | Internal refinement | R&D | 2017-02-04 |  | Not Started | see email "rotations refined synchronization"
Thesis | Update and submit thesis | W | 2017-02-18 |  |  | Will the degree be necessarily finished? How much time to presentation? Can I stay in the dorms till the end of the year?
projs selection | check initial improvement on nn50 | E | 2016-12-29 |  | In Progress